## Sheet1
Related User Story | Task Description | Priority | Assignees | Initial | Amount Remaining After…
|  | Level |  | Estimate | Week 1 | Week 2 | Week 3 | Week 4
Enter Test Result | 1. Design UI 2. Add functionality to be able to enter test results | 1
Store hashed passwords in the DB | 1. Add functionality to store hashed passwords for users in the DB (you may use any hashing mechanism --make sure to cite and credit the sources in comments) | 1
Admin query requests | 1. Design UI 2. Add functionality so that the administrator can pose queries in SQL and view the result in tabular format. | 1 | Ahmad | 16
Admin date reports | 1. Design UI 2. Add functionality so that the administrator should be able to select any two dates and view a report containing the information about all the visits during the time specified. The visit information should include the visit date, patient id, name, the names of the doctor and nurse involved, the tests ordered, test perform date, tests result abnormality, and diagnosis. The result should be sorted by the visit date followed by the last name of the patient | 1 | Ahmad | 14
BUGS ON UI | Fix where screen is cut off on some machines and others its not | 0
DEMO NOTES REVISIONS | manage_visit page: -should use case-insensitive search on the visit page, temp needs to have decimal points,**nurse should be loaded automatically **error messages for routine checkup are not showing.- **better to move format information for visit below the visit label - tests are ordered one by one --need to be order several tests together - should allow tests to be ordered anytime (remove the 15-min interval limit) | 0 | Ahmad | 6
| manage_appointments page: - error message on the appt time needs to be cleared, - search appointment needs to be clear about it's search by patient name - need to make the create appointment and search appointment page more clear so that user knows what to do | 0
| admin: -should make nurse's name editable - MD created a sp, but not called in the program - need to put candeletenurse and delete nurse in one transaction | 0
| - inactive nurse should not be able to login | 0
[5 empty] | 0 | 0 | 0 | 0