## Sheet1
Related User Story | Task Description | Priority | Assignee | Initial Estimate | Amount Remaining After…
|  | Level |  |  | Week 1 | Week 2 | Week 3 | Week 4
Implement login and logout functionality. Display full name and username of logged-in nurses on all views. | 1. Design login and logout pages (UI) 2. Create database access for nurse login/logout. 3. Display nurse's full name and username on all views. | 0 | Jabesi | 8 | 5 | 3
Develop the patient registration form. | 1. Design the patient registration UI. 2. Implement dropdown boxes for gender and state. 3. Perform field validation (zip code, phone number, etc.). 4. Create database access for patient registration. | 1 | Ahmad | 12 | 12 | 0
Implement the edit patient functionality. Patient information should be automatically loaded for updates. | 1. Design the edit patient UI. 2. Implement auto-loading of patient information. 3. Create database access for editing patient information. | 2 | Ahmad | 12 | 12 | 0
Admin functionality to add nurses to the system. | 1. Design the nurse addition UI for admins. 2. Implement dropdown for roles (nurse/admin). 3. Create database access for adding nurses. | 3 | Rahman
Create the database on the departmental MySQL server for the project. | 1. Email Edwin for database creation. 2. Write SQL statements to create tables. 3. | 0 | Rahman
Project set up: follow practice exercise 11 for setting up a good structure, using Data Access Layer (DAL) in MVC/MVVM. |  | 4 | Jabesi/Ahmad/Rahman | N/A
SQL Injection Mitigation: Use parameterized queries in C# or prepared statements in Java. |  | 4 | Jabesi/Ahmad/Rahman | N/A
Revise the database design |  | 0 | Ahmad | 2 | 0
|  |  |  | 34 | 29 | 3 | 0 | 0