## Sheet1
Related User Story | Task Description | Priority | Assignee | Initial | Amount Remaining After…
|  | Level |  | Estimate | Week 1 | Week 2 | Week 3 | Week 4
Search for a patient by criteria | 1. Add Search UI elements into the Manage_Patients form 2. Add functionality to search by date of birth, name (last and first), or both (note that the search should be done on the DB server side instead of the client side ) | 2 | Ahmad | 7 | 7 | 0
Create an appointment | 1. Design create appointment UI 2. Add functionality to create appointments and save them in the database(Double booking isn't allowed and appointments are 20 minutes long) | 1 | Jabesi | 14 | 5 | 6 | 4
Enter routine checkup information | 1. Design Routine Checks UI 2. Add functionality to enter routine checks information and store it in the database (keep in mind systolic, diastolic blood pressure and pulse are integer values, weight (lb), height (in) is a decimal value) | 1 | Rahman/Ahmad | 14 | 14 | 0
Search for patient to show his/her appointment information | 1. Design Search UI. 2. Add functionality to search for patients and display their appointment information (same search criteria as above) | 2 | Jabesi | 4 | 0 | 3 | 1
Edit Appointment if time has not passed | 1. Design edit appointment UI. 2. Add functionality to edit an appointment only if the time hasn't passed and save those changes to the database | 3 | Jabesi | 4 | 0 | 4 | 2
Display username | 1. Display username in the UI | 4 | Jabesi | 30' | 0 | 0 | 10'
Fix Add Nurse | 1. Fix the bugs with adding a nurse | 1 | Rahman/Ahmad | 4 | 4 | 0
Fix Nurse state text box | 1. Nurse state box should be a comboBox/dropdownBox instead of text box | 3 | Rahman
[5 empty] | 30 | 13 | 7 | 0