## Sheet1
Related User Story | Task Description | Priority | Assignees | Initial | Amount Remaining After…
|  | Level |  | Estimate | Week 1 | Week 2 | Week 3 | Week 4
Enter initial diagnosis and order tests for a visit | 1. Before the user confirms the tests ordered, the user can remove or add more tests to the order. Note that initial diagnosis is optional at the routine checkup stage. The nurse can fill in it later after the doctor exams the patient. 2. Design UI 3. Add functionality to enter intial diagnosis and order tests | 1
Enter Test results | 1. Design UI 2. Add functionality to be able to enter test results | 1 | Md Mostafizur Rahman | 5
Enter final diagnosis | 1. Once the final diagnosis is entered, patient visit information such as the checkup, tests, and diagnosis is read-only. Make sure to prompt the user about it for confirmation. 2. Design UI 3. Add functionality to be able to enter final diagnosis | 1
Search patients and view patients' visit information | 1. Search patients and view patients' visit information (e.g checkup info., tests ordered and/or performed including time, diagnoses, etc. 2. Design UI 3. Add functionality to search and view patients' visit information | 2
Admin edit/delete/deactivate nurse | 1. admin edit nurse (including updating nurse's password), delete nurse (if there is no visit associated with the nurse, otherwise, deactivate the nurse) 2. Design UI 3. Add functionality to edit nurse and delete/deactivate nurse | 1
Redesign the database. | Modifing the lab_test table and add permanent value too it. | 2 | Md Mostafizur Rahman | 2 | 1
[5 empty] | 1 | 0 | 0 | 0
ITERATION 4 DESCRIPTION NOTES:
note that please be concious about the user-friendlines of your program. It's not user-friendly if the user only sees ids without any detailed information. It's important that on all the views, it should be clear about the patient's name, dob doctor's name nurse's name Each team member must use at least one stored procedure for one of the DB operations for this iteration so that everyone may practice writing stored procedures and see how it helps you reduce the coupling of the SQL statement that would otherwise have been embedded in your code. Please have the stored procedures in the readme.txt file for easy access during the demo.